## Slide 1
CONTRACT MODIFICATION
18th November 2019, Montana, Bulgaria
19th November 2019, Giurgiu, Romania

## Slide 2: Contract modifications chapter 16 from the PIM
  Considering that the initial Application Form has been evaluated and selected by the Monitoring Committee it is strongly advised that partners limit the number of changes of a project.

## Slide 3: Contract modifications
  Changes which do not require the signing of an addendum to the subsidy contract – Notifications (Subsidy contract art. 13 para. 7)
  Changes which require the signing of an addendum to the subsidy contract (Subsidy contract art. 13 para. 4)

## Slide 4: Contract modifications
  Notification = minor changes which do not alter in a significant way the approved Application Form.
  The JS will analyse the request in order to verify if it does not fall under one of the cases for which an addendum to the subsidy contract needs to be signed.

## Slide 5: Contract modifications Notifications
  Examples
  contact data change;
  change of the bank account of the LB;
  modification of the name of the beneficiary (without changing the identification number of the institution);
  minor changes in the application form;
  material errors in the text of the contract.

## Slide 6: Contract modifications Addenda
  Changes which have a major impact on the approved Application Form shall require the signing of addendum to the contract.
  Beneficiaries should try to limit these changes as much as possible, as they usually alter the initial financing conditions.

## Slide 7: Contract modifications
  Addenda
  Examples
  major changes in the Application Form;
  changes in the project partner organizations (name, headquarter, etc.);
  changes in the partnership (requires MC approval);
  Extension of the implementation period (requires MC approval);
  reallocation of funds between budgetary chapters (only in exceptional and duly justified cases).

## Slide 8
  with minimum 30 days before they intend to produce effects, to be submitted to the JS
  no later than 2 months before the end date of the implementation period

## Slide 9
  The requests for modification have to be submitted by the LB to the JS.
  The LB will initiate the modification request in the eMS system, submitting also an e-mail in the eMS system to the designated JS officers.

## Slide 10
www.interregrobg.eu
  LB submits the addenda (signed, stamped and dated) by post / courier / directly to MA.
  MPWDA representative signs the addenda and the send it to JS,
  JS will submit the addenda (including annexes) to the beneficiaries by post / courier.
  LB must upload the signed addenda and the annexes in eMS, section “attachments” in maximum 3 working days.