## Slide 1
Most Common Errors
in Project Reporting
18th November 2019, Montana, Bulgaria
19th November 2019, Giurgiu, Romania

## Slide 2
Common Errors
in Partner Reports
The partner report is filled in Bulgarian or Romanian, although the official language of the Programme is English;
The justification documents uploaded are named in RO or BG language, rather than EN, as required by the Programme; the name of the document does not reflect its content; or the file is not named at all;

## Slide 3
Common Errors
in Partner Reports
The partner report is submitted to FLC, although it does not include any expenditures;
The partners do not describe their individual contribution to the Project output indicators;
The partners do not describe their individual contribution to reaching the target groups;

## Slide 4
Common Errors
in Partner Reports
when reporting progress per WPs/Activities:
the progress in activities during the reporting period, which is not yet paid for, is not reported;
the progress in the activities is described in very general terms, without providing details on what has been done, by whom, when with what purpose and what effect/result;
when describing the progress in activities, the focus is placed primarily on documentary evidence, indicating the number of every single document issued in the procurement or acceptance of services and deliverables, without providing any information on the actual output, content, scope or objective of the activity.
The delays in the activities are not explained, or if explained, no solution/measures is presented in this regard in the dedicated section;

## Slide 5: Common Errors in Partner Reports
when reporting progress per Deliverables
  The partners do not add the deliverables that have registered progress in the reporting period; The partner reports contribution to a certain activity, but it is not reflected in the deliverable section, as the related deliverable is not added and properly described
  No deliverable evidence is provided or the documents uploaded as deliverable evidence (contract, invoice) do not attest the delivery of equipment or the provision of services;
  The description of the progress in the deliverable repeats the information provided for the progress in the activity;
The partners fill in the field “Deliverable description”, indicating the documents, uploaded as deliverable evidence, rather than describing and quantifying (if the case) the progress (specific equipment delivered or services provided) in the reporting period;

## Slide 6
Common Errors
in Technical Project Reports
The reporting period of the project report is not entirely covered by partner reports from all beneficiaries;
The progress reported in the partner reports is not entirely consolidated at project level in the technical project report
When consolidating the physical progress of the project, described by the partners in their individual partner reports, the LB copies the information provided mechanically, thus describing the progress per partners and sub periods, which results in discrepancies, duplicating of information, and generally incoherent and difficult to comprehend picture of the project physical progress;
Not all fields of the project report are filled in. For instance, if no general problems have been encountered in the project implementation, the dedicated field should be field in accordingly rather than left blank;
“Highlights of Main Achievements” – rather than focusing on the major outputs/achievements so as to provide an overall picture of the project implementation so far, the LB consolidates the information provided in project summary in each partner report for the period;

## Slide 7
Common Errors
in Technical Project Reports
Double-counting of people, when reporting target groups reached or project indicators (e.g. Population having access to joint employment initiatives) – one person, who has taken part in 2 events/actions is reported as 2 persons
The reported contribution to the Output indicators is not supported by evidence, uploaded in the dedicated field “Project Main Outputs” -> “Attachments”, and relevant description in the individual partner reports.
Project Beneficiaries do not pay the necessary attention to the reporting of the projects contribution to the “Horizontal principles”. Instead of describing the specific measures/efforts undertaken during reporting period in complying with and promoting the horizontal principles, they often provide some general information, referring to the project implementation as a whole, rather than to the specific reporting period;

## Slide 8
Common Errors
in Technical Project Reports
Target Groups reached:
The target groups reached are not reported at all, or, if reported, they are not split per categories, in accordance with the target group categories defined in e-MS and the Application Form (1st and2nd call);
the field “Description of target group” is filled in with the name of the target group category or some general reference,;
no verification sources are provided or indicated in the dedicated category;
some indicative figures in accordance with the size of the target group defined in the AF is reported, rather than the number of target group representatives, effectively reached in the project implementation during the reporting period;
project management team members or other partner representatives taking part in project events are reported among the target groups reached or as a contribution to the project indicators

## Slide 9
Common Errors
in Final Reports
The progress described in the last project report in e-MS covers the entire project implementation, rather than the last 6-month period
The Final Implementation Report is not submitted together with the final reimbursement claim (the last project report with expenditure);
The information provided per activities in the Final Implementation Report just consolidates the information reported per activities in the intermediary project reports, instead of providing an overview of the activity implementation focusing on the main outputs and results of the respective activity and their further use and contribution to the project implementation
The Final Implementation Report does not cover the entire period of the project implementation;
List of participants in trainings is not submitted with the Final Implementation Report, when the project included trainings.