## Public Procurement
Public procurement reporting
Project beneficiary | Type of contract | Object of the contract | Contract estimated value according with the approved budget (Euro without VAT) | Type of Procurement Procedure | Procedure launching number/date | Deadline for tender submission | Deadline for opening of the tenders | Current status of the procedure* | Estimated date for signing the contract | No. of tender anouncement | Estimated execution duration of the contract to be signed | Bidders (including all third parties) | SIN (single identification number for the company/legal person) | Contracted company | SIN (single identification number for the company/ legal person) for Subcontractors/third parties | Subcontractors/ third parties involved | Number of the works / supplies / service contract | Date of the works / supplies / service contract | Upload procurement documents (including signed contract) | Total eligible value of the contract (Euro VAT incl. if eligible) (Euro) | Deadline for the contract execution | Status of the contract | Modifications of the contract** (addenda) | Upload documents related to the modifications of the contract | Flat correction proposed by RO FLC | Date | Reason | Flat correction applied by BG FLC | Date | Reason | Flat correction proposed by AN | Date | Reason | Flat correction applied by AM | Date | Reason
Lead Partner | Services | ex. Technical project | 40000 | Call for tenders | 16879 / 20.05.2014 | 10.06.2014 | 30.06.2013 | Drop down: on-going/finalized/cancelled/appealed | 30.07.2014 |  | 3 months |  |  | SC XYZ LTD |  |  | 1 | 30.07.2014 | [upload] | 12898.77 | 1.02.2015 | on-going/ realized/cancelled | Add no. 1 / 10.10.2014 for extension of the contract duration from 1 months to 2 months |  | 10% | 30.07.2015 | Text 300 caractere | 10% | 30.07.2015 | Text 300 caractere | 5% | 30.07.2015 | Text 300 caractere | 10% | 30.07.2015 | Text 300 caractere
|  | [input text] | [20 empty] | [input text]
*the status of the procedure will be described , including apeals addressed to National Council for Solving Appleals (Ro), to the Commision for Protection of Competition (Bg), to MA/NA (Bg), or to justice courts
** Will be specified the object and the value (if case) of any addenda signed to the works/supplies/services contracts
Lead Partner | Works | 1. Direct procurement;
Partner 1 | Supplies | 2. Open procedure;
Partner 2 | Services | 3. Restricted procedure;
Partner 3 |  | 4. Competitive dialoque;
Partner 4 |  | 5. Negotiated procedure with prior publication of a contract notice;
Partner 5 |  | 6. Negotiated procedure without prior publication of a contract notice;
7. Call for tenders;
8. Public invitation;
9. Open procedure (Simplified rules);
10. Design contest
11. Own procedure
12. Other type of procedure